## A&M
# | Task | Objective | Data collection/ Data sources | Assessment, design & development | Deliverables
1 | Review - Data & Information | 1. Assessment of need for data and information | 1. Review of information available with DESL & public domain | 1. Preparation of table indicating data requirement against each task 2. Preparation of data formats | 1. Sub-Deliverable (SD) SD-1: Data formats
2 | Review of global development - EEDSM market transformation strategy & tools | 1. Identification of key condition precedents other than SE services for quick success in market transformation | 1. Short listing of few successful countries based on latest IEA report on Energy Efficiency Market 2. Review of reports on SE market transformation activities for these countries available in the public domain 3. Review of reports on SE market transformation activities available in the public domain | 1. Identification of key measures 2. Analysis of impact of these measures 3. Preparing a priority list having universal relevance 4. Preparation of report | 1. SD-2: Report on the global scenario on SE market transformation measures and their relevance for the SE market in Ghana
3 | Inception Mission | 1. Finalisation of work plan 2. Formation of SESC Development Advisory Committee (SDAC) | 1. List of key stakeholders 2. Stakeholders expectation from the project 3. Stakeholders contribution to the project 4. Sources and availability of data 5. Data sharing protocol 6. Copies of available reports on energy supply, demand, demand growth, shortages (peak & energy) 7. Copies of available reports on energy audit 8. Copies of reports from MiDA’s existing other programs of ‘Compact’ | 1. Data availability gaps 2. Strategy for collection of available data 3. Strategy for bridging data gaps 4. Strategy for managing impact of data gaps 5. Criteria for selection of members for SDAC 6. Identification of targeted sectors for SE intervention 7. Preparation of materials for kick-off meeting and inception presentations | D1. Inception meeting notes (kick-off meeting) D2a. Report on inception workshop D2b. Draft inception report D2c. Final inception report 3. SD-3: Document on key performance indicators
4 | Market assessment: Ghana EE DSM Market | 1. Assessment of energy efficiency investment potential | 1. Primary survey to bridge the data gap identified during the inception mission 2. Few walk through audits 3. Available reports from Governmental institutions & Development partners 4. Available reports on Standard & Labeling of Appliances (SLA) in Ghana 5. Available reports on penetration of solar photovoltaic systems | 1. Projection of demand-supply gaps 2. Profiling of energy consumption patterns & energy consuming appliances/equipment’s in the building & MSME sectors 3. Assessment of impact of the SLA program 4. Assessment of impact of solar roof-top program 5. Assessment of opportunities for Programatic projects for smaller buildings 6. Assessment of energy efficiency enhancement opportunities through improved practices and investment in technologies 7. Assessment of cost of implementation measures 8. Assessment of impact of efficiency measures in reducing demand and marginal cost of power generation 9. Assessment of overall benefits from efficiency measures (financial, economic, social & environmental) 10. Assessment of investment attractiveness considering financial returns & scalability 11. Rank ordering of investment projects 12. Assessment of overall investment potential and setting targets 13. Preparing annotated outline of the report for review by SDAC/MiDA 14. Preparing annotated outline of the report for review by SDAC/MiDA | 1. SD-4: Ghana SE market assessment report
5 | Global case studies - EEDSM market transfromation | 1. Identification of different strategies that have been successfully implemented in few countries for transformation of SE market | Review of: 1. Select list of countries from IEA report on EE market 2. Case study reports available in the public domain 3. DESL case study reports on SE market transformation consulting assignments | 1. Identification of different barriers 2. Barrier strategies 3. Evaluation of impact 4. Models of SE services and their impacts in different markets 5. Models of SE services and their impacts in different markets | 1. SD-5: Report on the global scenario on SE market transformation measures
6 | Assessment - Ghana SE market transformation needs | 1. Identification of SE market barriers& barrier removal strategy | 1. Inputs from the Ghana SE market assessment & Global SE market review reports 2. Other reports on Ghana SE challenges & strategy 3. Available reports from various Government agencies and Development partners 4. Primary survey involving SE product & service providers, Policy makers including Energy Commission (EC) | 1. Assessment of current status of penetration of EE & DSM measures in Ghana 2. Identification of barriers against faster & deeper penetration of SE market 3. Identification of various market transformation tools (policy, regulatory, utility tariff structure, financing, promotions, programs) relevant for Ghana market 4. Review of policy & institutional framework in Ghana for promoting SE market 5. Potential impact of individual measures on transforming the SE market 6. Estimation of potential impact of various tools and their contribution towards national SE goals 7. Stakeholders consultation | 1. D3.1: Report on Ghana SE market transformation need
7 | Assessment - Demand for SE services in Ghana SE market | 1. Assessment of the baseline condition of SE service market | 1. Inputs from Ghana SE market potential and Global SE market review reports 2. Interaction meeting with SDAC members & EC to identify potential stakeholders for SE services 3. Primary survey (SE-EE, DSM & Renewable Energy service providers, Energy Utilities, Facility managers for buildings, Industry associations) concurrently with the survey on ‘transformation needs’ 4. Walk through audits | 1. Preparing a list of different types SE services (SES) for market transformation 2. Assessment of applicability of different types of SE services for different sectors & segments in Ghana 3. Developing SES assessment methodology based on identified SE market potential in Ghana 4. Assessment of potentials for such services (volume & financial) and rank ordering | 1. Outputs would be used for preparing the SE services stock taking & gap analysis report
8 | Status quo - SE services in Ghana | 1. Identification of SE service providers & assessment of their capacities | 1. Outputs from previous tasks 2. Qualification and experiences of the service providers 3. Available reports on energy audit, feasibility study, project preparatory documents from the identified service providers 4. Annual reports of service providers-Business volumes-number of projects and financial turnovers 5. Number of service providers following quality management/quality certification processes 6. Available reports on client feedback on services 7. Availability of SE financial mechanisms & capacity of lenders to finance EEDSM projects 8. Feedbacks from the stakeholders workshop | 1. Assessment of capacity to provide services under different models 2. Assessment of quality of reports & improvement needs | 1. SD-6: Draft report on SE services stocktaking & gap assessment 2. SD-7: Report of workshop on SE services stocktaking & gap assessment 3. D3.2: Final report on SE services stocktaking & gap assessment
9 | Status quo - Tertiary SES education program in Ghana | 1. Assessment of the baseline condition of SES education program in Ghana | 1. Reports/information available with Ministry of Education (Ghana Education Services), MiDA, EC and other development partners on the institutions providing tertiary education on SE services 2. Primary survey of the identified institutions (listed in the RFP and others), alumnus, clients 3. Copies of syllabi, course curricula, training programs, examination programs and certification programs from the prospective SESCs 4. Historical records of program outputs including number of trained/certified professionals by the existing institutions in Ghana 5. Primary survey of available facilities (hardware & software) for representative institutions 6. Outputs from SE services stocktaking and gap analysis reports | 1. Analysis of the objective and context of the existing tertiary education being provided by different institutions in Ghana 2. Historical development & performances evaluation as per the developed KPI 3. Performance analysis for the alumnus of the institutions in the market place 4. Feedback from the recipient of services 5. Appraisal of program/study reports 6. Determination of baseline | 1. SD-8: Report on baseline review of tertiary education program in Ghana
10 | Global development alternative models on tertiary education and certification programs | 1. Identification of global best practices | 1. Reports available in the public domain 2. Reports from DESL & partners’ consulting assignments on development of EE curriculum and SES professionals 3. Tertiary education curriculum & examination programs of DESL’s partners 4. DESL’s own program ‘Project Analyst Trainee (PAT)’ | 1. Historical analysis of the development of different models 2. Analysis of impacts 3. Comparative analysis against benchmark practices in more matured market (e.g. India, Singapore) 4. Assessment of gaps in the context of requirement in Ghana SE market | 1. SD-9: Report on global practices on tertiary education program for SE services 2. D3.3: Report on baseline review and gap assessment of tertiary SES education program in Ghana
11 | Development of value model - SE Services | 1. Developing market for the SESC services | 1. Inputs from reports on market assessment & needs for SE services for market transformation 2. Global case studies available in the public domain 3. DESL case studies | 1. Assessment of ‘ready-to-go’ market for SE services in Ghana 2. Identification and evaluation of potential revenue earning streams from SE services 3. Assessment of potential benefits from such services for different stakeholders (SESCs, Consumers, Utilities & the Country) from the ‘ready-to-go’ market 4. Assessment of policy and other supports required for catalyzing market development 5. Developing an agenda for the SESCs to work with different stakeholders including policy makers, regulators and development partners for developing market for SE services in Ghana | 1. SD-10: Report on value model for SE services
12 | Preparation of SESC roadmap | 1. Promoting development of SESCs in Ghana | 1. Inputs from various reports 2. Reports on global case studies available in the public domain 3. DESL case studies 4. Case study reports from other consortium members | 1. Development of logical framework (Goal, Input, Output, Outcome and Impact) 2. Development of key performance indicators (KPIs) for each of the element of the KPIs 3. Development of an institutional framework for implementation of roadmap 4. Development of M&E framework 5. Preparation of a draft roadmap matrix-what to be done by when and who would be the key stakeholders involved in implementation and monitoring 6. Consultation with SDAC 7. Preparation of draft roadmap 8. Preparation of presentation material for market accelerator conference 9. Finalisation of roadmap post conclusion of conference & trade show | 1. D3.4: SESC road map
13 | Preparation of Tertiary level SES program roadmap | 1. Periodic review and updating of tertiary level program | Inputs from: 1. Report on baseline review of tertiary education program in Ghana 2. Report on baseline review and gap assessment of tertiary SES education program in Ghana 3. Report on global practices on tertiary education program for SE services 4. Case study reports from consortium members 5. Feedbacks from the national workshop on SES program roadmap | 1. Development of logical framework (Goal, Input, Output, Outcome and Impact) 2. Development of key performance indicators (KPIs) for each of the element of the KPIs 3. Development of an institutional framework for implementation of roadmap 4. Development of M&E framework 5. Deliberations during workshop on SES program roadmap | 1. SD-11: Report on consultative workshop 2. 3.5: Report on the tertiary level SES program road map
14 | 1. Design & implementation of national SE market accelerator conference | 1. Solicit interest in National SE Market opportunities and provide a constructive platform for a dialog on National SE Market development ideas | Engagement with SDAC for: 1. List of key stakeholders & invitees 2. List of speakers & panelists 3. Tools for dissemination 4. Engagement with event managers in Accra 5. Venues & logistics 6. Cost structure for such workshops in Ghana 7. Physical survey of venue alternatives | 1. Expected outcome from the conference & workshops 2. Review of dissemination strategy for maximizing stakeholders participation 3. List of topics and modules 4. Design of programs and scheduling 5. Preparatory activities & schedule 6. Costing 7. Preparation of plan & budget 8. Review of feedback from workshop participants 9. Review of SESC and SES program roadmaps and modification | 1. D 4.1: Report on design and implementation of plan for the national SE market accelerator conference
15 | 1. Design & implementation of regional SE technology trade show | 1. Provide an opportunity for local and National SE market actors to showcase innovative SE related service models, initiatives, and new technologies to the public | 1. Reports on availability of innovative SE products & services in the region 2. Primary survey-availability of innovative SE products & services in Accra 3. Primary survey-Banks on innovative financing mechanisms for SE or any other new programs | 1. Expected outcome from the trade show 2. Assessment of potential benefits for participants 3. Preparation of a database of potential participants 4. Assessment of preparatory time required for participants 5. Review of facilities to be provided by the host to the participants 6. Review-criteria for selection of participants 7. Assessment of venue availability and need for development of infrastructure 8. Design of programs 9. Preparatory activities & schedule 10 Costing 11. Preparation of plan & budget 12. Methodology for obtaining participants feedback 13. Methodology for remaining engaged with participants for development of the market for SE product & services 14. Conducting of the trade show 15 Review of feedback from the participants and the visitors to the show | 1. D4.2: Report on design & implementation plan for the regional SE technology showcase 2. D4.3: Report on implementation plan for the national SE market accelerator conference and regional SE technology showcase
16 | Development of se course syllabi (SEMP, SEAP, EAP) | 1. Preparing the topics & outlines to be covered under the certification examination program | 1. Targeted professionals and eligibility criteria for candidates Inputs from: 2. Specific inputs from the TOR 3. Report on baseline review of tertiary education program in Ghana 4. Report on baseline review and gap assessment of tertiary SES education program in Ghana 5. Report on global practices on tertiary education program for SE services 6. Case study reports from consortium members 7. Inputs from consultation with key stakeholders (EC, MoEn, and other institutions recommended by MiDA) | 1. Preparing a long list of subjects to be covered under the syllabus 2. Review of syllabus content for energy managers & energy auditors 3. Review of the need priority of the SE market for energy audit and technical interventions 4. Review of the qualification and eligibility criteria for candidates 5. Assessment of the specific need for education and training for building capacities 6. Review of the existing syllabus of the prospective SESCs 7. Assessment of education and training need of the potential candidates 8. Comparative evaluation of different course & certification programs 9. Short listing of the subjects and development of the contents 10. Development of quality protocol 11. Preparation of draft syllabi | 1. SD-12: Recommendation report on qualification criteria for certification of SEMP, SEAP & EAP professional 2. D5: Report of SE course development syllabi
17 | 1. Development of se certification course contents (SEMP, SEAP, EAP) | 1. Detailed courses for the certification program | 1. As in case of previous module | 1. As in case of previous module | 1. SD-13: Report on dissemination workshop on the course development process & summary of courses 2. 6.1: Report on SEMP certification course content 3. 6.2: Report on SEAP certification course content 4. 6.3: Report on EAP certification course content
18 | Design of certification examination course (SEMP, SEAP, EAP) | 1. Selection of SESCs during the assignment period and certification of professionals in an ongoing manner | 1. Specific inputs on course development from the TOR 2. Reports on energy auditors certification examination program available in the public domain 3. Case study reports from consortium members | 1. Pros and cons analysis-written test vs written test followed by viva review i) Number of papers & scores ii) Common papers for all the three courses and the differentiated ones iii) Qualifying marks for passing & certification iV) Remedy in case of failures v) Validity & process of revalidation vi) Physical vs on-line examination vii) Proctoring for physical & online programs viii) Fee structure 2. Development of instruction book 3. Development of multiple choice questions-three versions each 4. Stakeholders consultation | 1. SD-14: Presentation to SDCA on draft examination program 2. D7.1: Report on SEMP certification course examination 3. D7.2: Report on SEAP certification course examination 4. D7.3: Report on EAP certification course examination
19 | Development of TOT course syllabi and tot courses (SEMP, SEPDP, EAEPT) | 1. Developing a cadre of trainers for providing training to the candidates intending to take certification examination | 1. Specific inputs on syllabi content as provided in the TOR 2. Inputs from the report on different certification courses 3. Videos of model and relevant TOT programs available in the YouTube 4. Reports on training programs and TOT training programs of the consortium partners | 1. Methodology for evaluation of effectiveness TOT course & programs 2. Evaluation methodology for assessing performance of individual trainers 3. Sensitivity analysis and design of review and feedback system 4. Preparation of PPT presentation 5. Preparation of instruction and tip sheets 6. Program development | 1. D8: Report on TOT course syllabi 2. D9.1: Report on SEMP TOT course content 3. D9.2: Report on SEAP TOT course content 4. D9.3: Report on EAP TOT course content
20 | Selection of SESCs
21 | Development of criteria for selection of SESCs | 1. Developing a transparent selection process | 1. Inputs primarily from the MiDA compact procurement process 2. Report on SESC roadmap 3. SDAC consultation 4. Consultation with few potential SESCs | 1. Criteria for scoring of institutions 2. Criteria for scoring of individual training candidates for different certification examination 3. Review of baseline situation 4. Assessment-weight factors (SEMP, SEAP, EAP) 5. Weight factors for institutional scores & individual scores 6. Overall scoring 7. Preparing recommendation report for SDAC for finalisation of selection criteria 8. Providing support to SDAC for finalisation of the criteria | 1. SD-15: Recommendation report on criteria for selection of SESCs
22 | Development of RFP documents for selection of SESCs, bidding& short listing | 1. Alignment with MiDA procurement process | 1. MiDA RFP template | 1. Bid evaluation & selection criteria 2. Bid management process 3. Schedules 4. Data sheets 5. Assisting MiDA in issuance of RFP 6. Assisting MiDA for evaluation of bids and short listing of candidate institutions & training candidates | 1. D12.1: Documentation to support call for proposal to host the SESCs 2. D10.1: Report on proposals received from candidate organisation to host the SESCs & scores for short listing 3. D10.2: Report on short list of qualified candidate organisations & training candidates
23 | Conducting certification examinations (SEMP, SEAP, EAP) | 1. Scoring for selection of host SESCs 2. Evaluation of course & examination process | 1. Reports on proctoring alternative models available in the public domain 2. Database of consortium partners 3. Feedbacks from the training candidates | 1. Review of different proctoring practices 2. Stakeholders consultation 3. Development of multiple-choice questions (MCQs) from the course material 4. Review of available laboratory, instruments and test facilities for EA examination 5. Conducting of examinations 6. Development of structured format for obtaining feedback from candidate institutions & training candidates on the courses & examination process 7. Review of the courses, MCQs & examination process 8. Identification of improvement needs 9. Consultation with SDAC 10. Finalization of course implementation plan | 1. SD-16: Recommendation report on proctoring 2. D11.1: Report on Ghana SEMP course certification examination results 3. D11.2: Report on Ghana SEAP course certification examination results 4. D11.3: Report on Ghana EAP course certification examination results 5. D11.4: Report on SEMP course implementation 6. D11.5: Report on SEAP course implementation 7. D11.6: Report on EAP course implementation
24 | Selection of SESC | 1. Selection of two hosts SESCs | 1. Institutional score sheets 2. Examination score sheets | 1. Assisting MiDA in preparing the composite & final score sheets 2. Rank ordering of the qualified candidates 3. Development of ‘MOU’ to be signed between MiDA & the candidate institutions 4. Facilitating interaction meetings between MiDA & selected institutions 5. Selection of 2 candidates to host SESCs 6. Facilitating signing of MOU | 1. SD-17: Draft MOU 2. D12.2: Report on final selection of SESCs host institutions
25 | Review & recommendation-tot courses (SEMP, SEPDP, EAEPT) | 1. Evaluation of the TOT implementation & identification of improvement measures | 1. Monitoring of video 2. Feedback from candidates | 1. Conducting of TOT programs 2. Development of structured format for obtaining feedback from candidate institutions & training candidates on the TOT courses & delivery process 3. Review of the courses 4. Identification of improvement needs 5. Consultation with SDAC 6. Finalization of course implementation plan | 1. D13.1: Report on the SEMP TOT course implementation 2. D13.2: Report on the SEPDP TOT course implementation 3. 13.3: Report on the EAEPT TOT course implementation
26 | Development of business plans for SESCs | 1. Sustainable performances of the SESC | 1. Outputs from different tasks: 2. SE market assessment 3. SE market transformation need 4. SE services stocktaking & gap assessment 5. Value model for SE services 6. SESC roadmap 7. National SE market accelerator conference 8. DESL consulting reports on business planning for different entities 9. DESL own business development case reports 10. Reports on business plan on setting up new energy services businesses available in the public domain 11. Government documents on legal & statutory requirements 12. Case study reports from the selected SESCs 13. Stakeholders’ consultation | 1. Preparing the annotated outline of the plan and assisting SESC develop draft plan 2. Conducting business planning workshop 3. Handholding for finalization of the plan 4. Preparation of the final plan and presentation to SDAC | 1. SD-18: Draft business plan & report on business plan workshop 2. D14.1: Report on the SESC business plan
27 | Development of operation plans for SESCs | 1. Standardization of activities for achieving the targets and goals as per business plan | 1. Inputs from business plan 2. Interaction meeting with institutions authorities on the existing administrative processes & procedures 3. DESL operation manual | 1. Analysis of the current internal processes for organisation management 2. Development of processes for: i) Internal management ii) External management iii) Process automation & digitalization 3. M&E framework for review performance against business plan 4. Development of operational plan template 5. Assisting SESCs in documenting all the processes as per template and preparation of manuals 6. Preparation of check lists: i) Completion of documents ii) Quality assurance | 1. D14.2: Report on SESC operation manual
28 | Energy audit pilot | 1. On the job training on different types of energy audit | 1. Templates of different types of audit from DESL database 2. Particulars of building for audit obtained from MiDA | 1. Formation of audit team 2. Providing half a day refresher training on different types of audit including use of portable instruments 3. Review of availability of portable instruments 4. Mentoring on: i) Preparation of data formats and plan for data collection ii) Tabulation and organisation of collected data iii) Field measurements iv) Calculation routines v) Assessment of energy consumption and identification of energy savings projects vi) M&V for baseline & project performance evaluation vii) Project implementation strategy including management of EPC & financing viii) Preparation of PPT presentation ix) Preparation of reports 5. Review post completion of audit 6. Approach & methodology i) Quality of audit ii) Quality of presentation & reports | 1. D15.1: Report on critique of the walk through audits for each facility assigned to each of the SESCs 2. 15.2: Report on critique of the investment grade audits for each facility assigned to each of the SESCs 3. D15.3: Report on critique of the project implementation plans for each facility assigned to each of the SESCs 4. D15.4: Report on critique of the measurement & verification plans developed for each facility assigned to each of the SESCs 5. 15.5: Report on critique of the finance plan for implementation of SE projects 6. D15.6: Report on critique of the tender documentation for procurement of design and construction services to implement SE projects 7. D15.7: Summary report detailing all the project development documents for the pilot SE projects (Deliverables 15.1-15.6)
29 | Course delivery pilot | 1. Developing training skill of SESC trainers | 1. Videograph of one program each 2. Feedback from participants | 1. Assisting in design of the course based on finding from the audits 2. Development of the performance evaluation criteria and sensitizing the trainers 3. Selection of the first facility for course delivery in our presence 4. Review of observations made during the course delivery 5. Review of the Videograph 6. Preparation of review reports | 1. D16.1: report on written critique for each of the two SE courses delivered by each of the SESC 2. D16.2: Report on critique of the videotape playback for each of the two SE courses delivered by each of the SESC
30 | Review & revise-SESC road map |  |  |  | 1. SD 19: Final report on SESC roadmap 2. SD 20: Final report on SES program roadmap
31 | Develop final completion reports for Setting-up of Sustainable Energy Auditing Centers |  |  |  | 1. D17: Final completion reports for summarizing part I-III.
Note on F4: R Rajmohan: D-1 should be by the end of first week; Deliverables 2 to 4 mentioned in the proposal should be read as 2 series

## TECH10V2
|  | 2 |  | 4 | 6 | 8 | 10 | 12 | 14 | 16 | 18 | 20 | 22 | 24 | 26 | 28 | 30 | 32 | 34 | 36 | 38 | 40 | 42 | 44 | 46 | 48 | 50 | 52 | 54 | 56 | 58 | 60 | 62 | 64 | 66 | 68 | 70 | 72
# | Task/ Activity | M-1 |  | 6: M-2; 10: M-3; 14: M-4; 18: M-5; 22: M-6; 26: M-7; 30: M-8; 34: M-9; 38: M-10; 42: M-11; 46: M-12; 50: M-13; 54: M-14; 58: M-15; 62: M-16; 66: M-17; 70: M-18
H1 | bar: 4 to 72
0 | INCEPTION ACTIVITIES
1 | Review of data and information
1.1 | Preparation of a table showing the data requirement against individula task
1.2 | Preparation of data formats for the followings (Ghana baseline)
1.2.1 | Current energy situation & demand supply gaps | NR
1.2.2 | Sectoral energy consumptions | NR
1.2.3 | Market potential for SE products | NR
1.2.4 | Market potential for SE services | ?
1.2.5 | Need for market transformation | ?
1.2.6 | Investment potential for SE products & services-MSME industries | ?
1.2.7 | Investment potential for SE products & services-buildings | ?
1.2.8 | Potential for distributed solar PV system for buildings | NR
1.2.9 | Investment potential for solar PV systems in buildings | NR
1.2.10 | Availability of SE products | Done
1.2.11 | Need for and availability of SE services | ?
1.2.12 | Tertiary education system for EE & RE services | ?
1.3 | Review of information available with Consultants Team
1.4 | Review of information available in public domain
1.4.1 | Current energy situation & demand supply gaps
1.4.2 | Energy situation in target sectors
1.4.3 | Main drivers of demand -supply gap
1.4.4 | Potential for energy intensity reduction in target sectors
1.4.5 | Feasibility for on-site renewable energy
1.4.6 | Techno-economic feasibility of specific DSM measures that can be taken up
1.4.7 | Legal and Regulatory assessment in the context of SE
| SD-1: Data formats | W2
2 | Review of global development- EE DSM strategies & tools
2.1 | Shortlisting of a few focus countries (based on web research)
2.1.1 | Prepare a list of reports available for different countries
2.1.2 | Prepare a capsule summary on development of SE market
2.1.3 | Identify the strategies & tools used by different countries
2.1.4 | Capturing the lessons relevant for Ghana SE market
SD-2: Report on global SE market strategies & tools
W2
3 | Developing KPIs for defining the baseline
3.1 | Develop long list of baseline KPI for SE Services
3.2 | Develop long list of baseline KPI for tertiary education
3.3 | Develop long list of baseline KPI for SESC
| SD-3: Report KPIs for SE Services, SE Tertiary Education and SESC | W2
4 | Kick off meeting with MiDA
4.1 | Preparing for kick-off meeting
4.1.1 | Preparing PPT presention on: | bar: 4
Agenda for the kick-off meeting
Our understanding of the objective of the project
Proposed approach & methodology
Data & information requirements & formats
Bibliography of materialsaccessed from net
Stakeholders & consultation process
Broad work plan-deliverables & schedule
4.1.2 | Preparation of background note & PPT on suggestions
KPIs for SESCs, SE services, SE tertiary education
Global development on SE market transformation & relevance for Ghana
Business value proposition for the SESCs
Alternative models on tertiary education
Single step bid for selection of SESCs
Study tour for selected SESCs
4.1.3 | Organising kick-off meeting
Request MiDA for:
Finalising list of key stakeholders including chair & list of invitees for KOM
Venue & schedule for KMO
Issue of notice for meeting
4.1.4 | Conducting of meeting
4.1.5 | Preparation & submission on record notes of KOM
4.1.6 | Finalization of work plan for inception mission | bar: 4
4.1.7 | D-1: Prepare and submit kick off meeting notes | bar: 4
5 | Inception mission | bar: 4
5.1 | Stakeholders consultation (For inception work) | bar: 4
5.1.1 | Freezing the list of key stakeholders from perspective of data collection (SE market, MT need assessment, SE services, SE tertiary education) | bar: 4
5.1.2 | Sharing of findings from the initial work on baseline (Informal-one-on-one) | bar: 4
5.1.3 | Finalisation of plan for data collection (Secondary serach & survey) | bar: 4
5.2 | Data collection-field
5.2.1 | Identification of key sources of data/reports (MiDA, Utility, EC, Technical institutions, Ministries, other development partners)
5.2.2 | Collection of available reports (Energy scenario, energy audits, relevant reportsfrom MiDA & other reports on development of SE market& services)
5.3 | Data adequacy analysis
5.3.1 | Review of the reports & identification of data gaps
5.3.2 | Planning for primary survey for bridging the data gaps
5.4 | Primary data collection (Survey, audit, interviews)
5.4.1 | Finalisation of Plan for primary survey (Identification of facilities, market, companies, institutions, individuals), samples, schedule, technology & communication in consultation with MiDA
5.4.2 | Formation of field teams (Survey, audits, interviews)
5.4.3 | Training of field teams
5.4.4 | Survey-appliance market
5.4.5 | Walk through audit of few buildings in the residential & commercial segments
5.4.6 | Walk through audit of few MSME industries
5.4.7 | Review meeting with SESC tertiary educational institutions and inspection of training facilities including laboratories & testing equipments
5.4.8 | Review meeting with few identified SESCs/relevant service providers
5.4.9 | Interviews with select list of key stakeholders (Policy makers, Regulators, Building & Industry trade bodies, development partners)
5.5 | Developing strategy for stakeholders' engagement
5.5.1 | Stratification of stakeholders (Domains, direct, indirect, primary, secondary) | bar: 4
5.5.2 | Mapping of stakeholder expectations (need benefit analysis) | bar: 4
5.5.3 | Preparing plan for formal and informal engagement with different stakeholders during the different phases on the work (Consultation matrix) | bar: 4
5.5.4 | Development of engagement protocol (communication framework & matrix) | bar: 4
5.5.5 | Criteria for selection of members of SDAC | bar: 4
5.5.6 | Develop terms of reference for the SDAC | bar: 4
5.5.7 | Assist MiDA for formally notifying the formation of SDAC (preparation of the document) | bar: 4
5.5.8 | Preparation of PPT on staskeholders engement strategy including SDAC for presentation in inception workshop | bar: 4
5.6 | Organize and conduct one -day inception workshop | bar: 4
5.6.1 | Finalise the annotated outline of the inception report | bar: 4
5.6.2 | Finalise the agenda in line with report outline & in consultation with MiDA/SDAC | bar: 4
5.6.3 | Provide assistance to MiDA & facilitate conducting of the inception workshop | bar: 4
5.7 | Preparation and submission of report on workshop (Record notes) | bar: 4
5.8 | Preparation and submission of draft inception report | bar: 4
5.9 | Revision of Report based on MiDA feedback | bar: 4
D-2.1 : Submission of report on inception mission workshop | bar: 4
D-2.2 : Submission of draft inception report | bar: 4
D-2.3 : Submission of final inception report | bar: 4
I | DEVELOPMENT OF NATIONAL SESC ROAD MAP & DEVELOPMENT OF TERTIARY EA COURSE CURRICULUM FRAMEWORK
SE market transformation needs assessment
6 | Ghana EE DSM Market- Market Assessment
6.1 | Carry out in-depth analysis :
6.1.1 | EE&DSM policies & program & their imapct
6.1.2 | EE products& their penetration
6.1.3 | EE projects-retrofits buildings & implementation status
6.1.4 | EE projects-retrofits MSME industries & their implementation status
6.1.5 | Solar PV projects-retrofits
6.1.6 | Development of a SE project pipeline
6.1.7 | Investment analysis
6.1.8 | Marginal analysis-DSM and supply side management
6.1.9 | Analysis of potential impact of DSM measures-economic, social & environmental
6.1.10 | Assessment of other enabling environment for promotion of SE market such as:
Government policies
Legal & regulatory instruments
Utility DSM programs
Utility tariff
Availability & access to finance
Availability & reliability of SE products & services
Consumer capacity to absorb SE technologies
6.1.11 | Identification of current sources of sustainable energy services financing available in the market and complimentary technical assistance schemes
6.1.12 | Assessment of status quo on absorption of available finance in SE projects
6.1.13 | Assessment of capacity of the lenders to appraise and finance SE projects
6.1.14 | Identification and assessment of any innovative financial product that has been introduced in the Ghana market in the last five (5) years
6.1.15 | Assessment of overall institutional framework for development of SE market
6.1.16 | Assessment of overall investment potential & market drivers | bar: 8
SD-4: Ghana SE Market Assessment Report | bar: 8
6.2 | EE DSM Market transformation needs - Global case studies | bar: 6
6.2.1 | Review of IEA reports of EE market for select list of countries | bar: 6
6.2.2 | Review of case studies available in public domain | bar: 6
6.2.3 | Review of case studies from Consultants previous assignments | bar: 6
6.2.4 | Identification of different drivers in different markets | bar: 6
6.2.5 | Summarise lessons learned & relevance for Ghana | bar: 6
SD-5: Report on the global scenario on SE market transformation needs | bar: 6
6.3 | Ghana SE market transformation needs assessment
6.3.1 | Review
Contry stratgic & operational plan for the energy sector
Impact of energy availability & cost on economic development
Country strategy on combating climate change
Legal & regulatory initiatives on SE development
Strategy for EE and RE (Solar PV)
6.3.2 | Assessment of potential impact of identified SE opportunity on country's energy & climate change strategy
6.3.3 | Review the findings against global development
6.3.4 | Assessment of barriers against deeper penetration of EE & DSM measures in Ghana
6.3.5 | Identification of various market transformation tools (policy, regulatory, utility tariff structure, financing, promotions, programs) relevant for Ghana market
6.3.6 | Review of policy & institutional framework in Ghana for promoting SE market
6.3.7 | Preparation of adiscussion paper on needs for SE market transformation and strategy
6.3.8 | Stakeholders consultation
D3.1-Report on Ghana SE Market Transformation Needs Assessment | bar: 8
7 | SE Services stocktaking and gaps assessment
7.1 | Assessment of Demand for SE Services in Ghana
7.1.1 | Review of the lessons learned from the global development and assess their relevance for Ghana for SE services for transformation of SE market
7.1.2 | Listing of different types of SE services and their potential impact on SE market transformation
7.1.3 | Assessment of potential for such services (volume and financial) and rank ordering | bar: 8
7.2 | Status Quo of SE Services in Ghana
7.2.1 | Identification of key players in the SE services market in Ghana as presurvey/review carried out during inception mission
7.2.2 | Identification and evaluation of lenders providing financing for SE products, projects & services
7.2.3 | Developing a matrix of SE services priority (established from demand assessment study) & operating service providers
7.2.4 | Summarise findings from review meeting with SES service centres/service providers | bar: 6
7.2.5 | Review of available reports - energy audits, feasibility studies, project preparatory documents | bar: 6
7.2.6 | Annual and other reports of service providers | bar: 6
7.2.7 | Client feedback for services | bar: 6
7.2.8 | Market awareness-qualification & experiences of current SE service providers | bar: 6
7.2.9 | Assessment of capacity to provide services under different models | bar: 8
7.2.10 | Assessment of quality of reports and improvements needed | bar: 8
Preparation of proposal for SE services | bar: 8
Energy audit & diagnostic studies | bar: 8
Investment grade energy audit report | bar: 8
Baseline, baseline adjustment & M&V protocol | bar: 8
Financing of SE retrofit projects | bar: 8
Project monitoring & evaluation reports | bar: 8
Report on market transformation & development | bar: 8
7.2.11 | Preparation of assessment report including
Capacity of market actors needed to support project development in the private and public sector. | bar: 8
Assessment of capacity building needs | bar: 8
7.2.12 | Preparation of a PPT presentation for stakeholders consultation | bar: 8
7.2.13 | Stakeholers consultation & summarisation of feedback | bar: 8
SD-6: Draft report on SE services stocktaking & gap assessment (PPT format) | bar: 8
SD-7: Report of workshop on SE services stocktaking & gap assessment | bar: 8
D3.2-Report on SE Services Stocktaking and Gaps Assessment | bar: 8
8 | Perform a baseline review and gap assessment of tertiary SES education programs in Ghana
7.1 | Assessment of skill requirement for SES services in Ghana
8.1.1 | Conducting structured survey for assessing the need for skilled professional by the SE service providers in the following domains:
SE related professional organizations (e.g. areas such as architecture, engineering).
Existing, major SE related service Consultant or organizations.
SE related equipment suppliers (e.g. HVAC, pumps, solar systems, etc.).
Utility demand side management organizations.
Development partners.
8.1.2 | Stratification of skill needs under different education modules
Strategic energy management
Energy audit, diagnostic studies & project development
Practical work-using testing facilities, equipments in laboratories & on the job
8.2 | Assessment of need for tertiary education
8.2.1 | Analysis-need for tertiary education to meet the need of SE providers
8.2.2 | Analysis-potential impact of tertiary education for creating demand for SE services
8.2.3 | Training need assessment
8.2.4 | Assessment of need priority for tertiary education in Ghana
8.3 | Status Quo of Tertiary SES Education Program in Ghana
8.3.1 | Summarise the findings from the interaction meetings with key stakeholders (including institutions & alumnus) on tertiary education during inception mission
8.3.2 | Review of reports, documents collected during the inception mission on tertiary education
Course curriculum, syllabi,training program, examination and certification program provided by recognised institutions | bar: 6
Other training programs conducted by development partners, private bodies | bar: 6
Historical development-tertiary education for SE services | bar: 6
8.3.3 | Review & analysis-objective of the current pograms on tertiary education | bar: 6
8.3.4 | Assessment of the effectiveness of the current programs against identified needs | bar: 6
8.3.5 | Informal interaction with few identified alumnus & other SE service providers on the findings | bar: 6
8.4 | Assessment of capacity of existing educators & capacity building need | bar: 6
8.4.1 | Conducting primary survey and confidential interviews | bar: 6
8.4.2 | Assessment of capacity to meet the demand for tertiary education | bar: 6
8.4.3 | Presentation of the result abstrating the identity of the interviewees | bar: 6
8.5 | Assessment of the laboratory and equipment facilities of the existinginstitutions | bar: 6
SD-8: Report on baseline review of tertiary education programs in Ghana | bar: 8
8.6 | Global development - alternative models of tertiary education and certification programs
8.6.1 | Review of information available in public domain | bar: 6
8.6.2 | Review of information from Consultants projects and internal training process/ courses | bar: 6
8.6.3 | Historical analysis of the development of different models | bar: 6
8.6.4 | Market analysis-creating demand for SE tertiary education | bar: 6
8.6.5 | Analysis of impact | bar: 6
8.6.6 | Comparative evaluation of different models and relevance for Ghana | bar: 6
SD-9: Report on global practices on tertiary education program for SE Services | bar: 6
8.7 | Comprehensive analysis from above two sub-tasks
8.7.1 | Comparative assessment of current SES tertiary programs against global practices | bar: 8
8.7.2 | carrying out a 'SWOT' analysis | bar: 8
8.7.3 | Analysis of adequacy of lab facilities and testing equipment's | bar: 8
8.7.4 | Assessment of need for improvements in: | bar: 8
Course curriculum & syllabi | bar: 8
Examination & certification system | bar: 8
Laboratories & testing equipments | bar: 8
Utilisation of laboratories & testing equipments | bar: 8
Training of trainers & teachers conducting the tertiary education programs | bar: 8
8.7.5 | Preparation of report on assessment (PPT presentation) | bar: 8
8.7.6 | Organize workshop for stakeholder consultation
8.7.7 | Finalize the gaps assessment report based on feedback
Deliverable 3.3: Report on Baseline review and gap assessment of tertiary SES education programs
9 | Develop Ghana SESC Roadmap
9.1 | Preparation of potential SESC function modules based on outputs from SES market SE tertiary education baseline analysis (SD-5, D-3.1, SD-6, D-3.2, SD-8, SD-9 & D-3.3)
SE tertiary education, examination & certification
Developing & conducting specific training programs for SE services market players
Policy research-providing supports to Policy makers & Regulators for development of market transformation policy tools
Facilitating implementation of SE market transformation policies
Providing SE services directly to Building & MSME industries
9.2 | Development of value model of SE Services
9.2.1 | Assessment of ‘ready-to-go’ SE market for different services in Ghana: | bar: 10
SE services | bar: 10
SE tertiary education services | bar: 10
Training & development of SE service providers | bar: 10
Policy research, analysis & dialogue | bar: 10
Legal & regulatory research & analysis | bar: 10
Promotional activities | bar: 10
9.2.2 | Identification and evaluation of potential revenue earning streams from SE services | bar: 10
9.2.3 | Assessment of benefits for different stakeholders from the ‘ready-to-go’ market | bar: 10
9.2.4 | Review of global case studies on revenue models for similar organisations | bar: 10
9.2.5 | Identification of priority market for SESCs based on lesons learned from global case studies | bar: 10
9.2.6 | Developing a strategy paper on potential revenue streams based on value analysis | bar: 10
SD-10: Report on value model for SE Services
9.3 | Preparation of SESC Roadmap
9.3.1 | Finalize projections for SESC Market in target sector & Investment Needs
9.3.2 | Develop the road map for SE market based on output from market and market transformation need assessment study (SD-4 & D3.1)
9.3.3 | Identify the market needs for training and energy services technical assistance to support project development in the public sector and in key, energy intensive areas of the private sector
9.3.4 | Prepare recommendations on the function modules for SESCs and rank order considering market need priority
9.3.5 | Development of logical framework (Goal, Input, Output, Outcome and Impact) | bar: 10 to 12
9.3.6 | Development of key performance indicators (KPIs) for each of the element of the KPIs | bar: 10 to 12
9.3.7 | Development of an institutional framework for implementation of roadmap | bar: 10 to 12
9.3.8 | Development of M&E framework | bar: 10 to 12
9.3.9 | Development of the framework for organisation & human resource development in line with services KPIs over time | bar: 10 to 12
9.4 | Stakeholders consultation | bar: 10 to 12
9.5 | Assessment & recommendations on enabling environment for development SES market & SESCs | bar: 12
9.5.1 | Summarise the lessons learned from the global development on policy initiatives for SE S market transformation & development of SESCs (SD-2) | bar: 12
9.5.2 | Prepare a recommendation note on the policy initiatives in Ghana for supporting development of SESCs | bar: 12
9.6 | Development of road map | bar: 12
9.6.1 | Finalise the time framework for the raod map in consultation with SDAC | bar: 12
9.6.2 | Prepare a detailed activity list (Education, market | bar: 12
9.6.3 | Prepare the functional dployment & institutional development matris | bar: 12
9.6.4 | Finalise the targets for internal and external outputs | bar: 12
9.6.5 | Finalise M&E framework | bar: 12
9.6.6 | Prepare PPT presentation on SESC road map for market accelerator conference | bar: 12
9.6.7 | Preparation of report on SESC road map | bar: 12
| D3.4-Report on SESC Roadmap |  |  | 12: W12
10 | Development of tertiary level SES program roadmap
10.1 | Development of an overall framework linking:
10.1.1 | SE market transformation to SES programs
10.1.2 | SES programs to SESC road map
10.1.3 | SES tertiary education to SESC road map
10.2 | Review & analysis of potential impact of specific SE services on SE market transformation based on imputs from market & baseline analysis (D-3.2, 3.2, 3.3 & SD-4 & 10)
10.3 | Rank ordering of the proposed SE services
10.4 | Development of SES program road map
10.4.1 | Development of logical framework (Goal, Input, Output, Outcome and Impact) | bar: 10
10.4.2 | Development of key performance indicators (KPIs) for each of the element of the KPIs | bar: 10
10.4.3 | Development of an institutional framework for implementation of roadmap | bar: 10
10.4.4 | Development of M&E framework | bar: 10
10.4.5 | Stakeholders consultation | bar: 10
10.4.6 | Preparation of the SES program road map | bar: 10
10.5 | Development of SES tertiary education road map | bar: 10
10.5.1 | Preparation of an overall tertiary education framework to provide all the identified SE services for transformation of SE market (Based on inputs from SD-4 and D-3.1 & 3.2) | bar: 10
10.5.2 | Review of skill requirement for providing various SE services as per the SES road map | bar: 10
10.5.3 | Review of the targeted professionals for skill developments for the different SE services | bar: 10
10.5.4 | Review of need for tertiary education for development of the required skill sets for the different professionals | bar: 10
10.5.5 | Development of prototype content of three tertiary level SES courses | bar: 10
Strategic energy management | bar: 10
Investment grade energy auditing | bar: 10
Energy systems equipments & measurement campaigns (Laboratory) | bar: 10
10.5.6 | Development of outline of program courses and rank ordering | bar: 10
Theoretical class room | bar: 10
Practical laboratory | bar: 10
Practical-field | bar: 10
10.5.7 | Development of logical framework (Goal, Input, Output, Outcome and Impact) | bar: 10
10.5.8 | Development of key performance indicators (KPIs) | bar: 10
10.5.9 | Development of an institutional framework for implementation of roadmap | bar: 10
10.5.10 | Development of M&E framework | bar: 10
10.5.11 | Stakeholders consultation | bar: 10
10.5.12 | Preparation of the road map | bar: 10
D3.5-Report on the SES Program Roadmap
| SD-11: Report on the SES tertiary education road map |  |  | 12: W12
10.6 | Facilitate review of courses by SESC development advisory committee | bar: 14
10.7 | Presentation of results in national workshop | bar: 14
SD-12: Report on consultative workshop
11 | Planning of National SES Market Accelerator Conference & SE Technology Showcase
11.1 | Preparatory work
11.1.1 | Articulation of the expectation from the conference & trade show on:
SE market in Ghana
SESC road map
SES program road map
SES tertiary education road map
11.1.2 | Assessment of potential benefits for participants in the conference & trade show
11.1.3 | Preparing database of potential participants
11.1.4 | Review & assessment of facilities/support expected by participants for attending the program
11.1.5 | Review of options for venue & logistics
11.1.6 | Identification of potential event manager for organising & managing the shows
11.1.7 | Preparation of communication & media plan for promoting the conference & trade show
11.1.8 | Finalisation of program kits and distribution plan
11.1.9 | Preparation and submission of budget to MiDA
11.1.10 | Finalisation of methodology for obtaining participants feedback & post show engagement
11.1.11 | Design & submission of program brochure to MiDA for printing & circulation
11.2 | Plan for the conference
11.2.1 | Preparation of list of topics & presentation modules
11.2.2 | Preparation of list of speakers/panelists including guest invitees
11.2.3 | Design of program & scheduling
11.3 | Plan for the trade show
11.3.1 | Review-criteria for selection of participants, products, displays (SE market players-products, services, local, regional, global)
11.3.2 | Physical arrangements & supports to be provided to the participants (Layouts, temporary construction etc)
11.3.3 | Logistics including travel, transportation, local hospitality, facilities
11.3.4 | Travel, transportation, local hospitality
11.3.5 | Marketing plan
11.3.6 | On-site marketing plan (Banners, Kits, Flyers, Signages)
11.3.7 | Requirement/availability of sponsors (Other development partners)
11.3.8 | requirement/availability of program partners (media, knowledge)
11.3.9 | Planning timeline
11.4 | Finalisation of implementation plan in consultation with MiDA/SDAC
11.4.1 | Organisation & roles & responsibilities for conducting of the workshop & trade show
11.4.2 | List of participants & program contents
11.4.3 | Stakeholders engagement strategy
11.4.4 | Media & communication plan
11.4.5 | Logistics & budget
11.5 | Preparation of implementation plan for Accelerator conference & trade show
| D4.1-Report on Design and Implementation Plan for the National SE Market Accelerator Conference |  |  | 16: W16
| D4.2-Report on Design and Implementation Plan for the National SE Technology Showcase |  |  | 16: W16
| D4.3-Report on Implementation Plan Report for the National SE Market Accelerator Conference and SE Technology Showcase. |  |  | 16: W16
11.6 | Organize and conduct conference and technology show case
11.6.1 | Finalisation of organisation matrix for conducting of conference & trade show | bar: 18
11.6.2 | Providing assistance to MiDA for procurement of materials/services as per budget | bar: 18
Conference & trade show venue, space, layout, temporary construction | bar: 18
Promotional & marketing materials | bar: 18
Booth management | bar: 18
Event management | bar: 18
Logistic management for trade show including shipping & drayage | bar: 18
Travel, transportation, local hospitality | bar: 18
Catering | bar: 18
11.6.4 | Provide assistance to MiDA for issue of invitation letters | bar: 18
11.6.3 | Co-ordinate various activities as per the role provided in the organisation matrix | bar: 18
11.7 | Preparation of dissemination report
11.7.1 | Review of feedback from workshop participants | bar: 20
11.8 | Review of feedback from the participants and the visitors to the show | bar: 20
11.8.1 | Review of SESC and SES program and SES Tertiary education roadmaps and modification | bar: 20
| D4.4 - Report on Final Part I Dissemination Workshop |  |  | 20: W19
II | SELECTION OF INSTITUTIONS TO HOST SESCs AND SESC TRAINING COURSE DEVELOPMENT AND DELIVERY
12 | Target professionals for certification under the different tertiary education module
12.1 | Assess the requirement of qualification & experience required for different types of SE services at different levels (Based on SD-8, SD-9 & D-3.5)
12.2 | Review the qualification and experience of the professionals currently engaged with SE service providers (part of structured survey)
12.3 | Review and assess the availability of professionals & their qualification & experience (from primary survey data)
12.4 | Stakeholders consultation
12.5 | Prepare a recommendation report on eligibility criteria for canditates for certification under different courses
SD-13: Recommendation report on qualification criteria for certification
12.6 | Development of prototype content of three tertiary level SES courses
12.6.1 | Preparing a table on learning goal at different phases of the SES tertiary education road map
12.6.2 | Review of the proceedings of the market accelerator conference (SES program & SES Tertiary education road map
12.6.3 | Review of the syllabi and course contents based on documents reveived from the existing institutions
12.6.4 | Preparation of a master matrix:
Phases as per road map
Learning goals at the different phases
SE service requirements
SE learning modules for the three courses (Common & differentiated under three courses, theoretical & practical)
12.6.5 | Analysis-need priority
12.6.6 | Stakeholders consultation
12.6.7 | Development of the outline for the priority courses
12.6.8 | Development of course administration guide
Course instructor minimum qualifications;
Course learning objectives;
Course participant qualification criteria;
Course topics and associated delivery timeframes;
Course delivery structure and method of instructions;
Certification exam format and proctoring arrangement;
Criteria for conferring the certification qualification
12.6.9 | Consultative meeting with SDAC
12.6.10 | Consultative workshop with key stakeholders
12.6.11 | Finalisation of the outlines of the three courses
SD-14: Report on workshop om the course development process and summary of the courses | bar: 8
D5-Report on Sustainable Energy Course Development Syllabi | bar: 8
12.7 | Development of course content for SEMP & SEAP for certification examination
12.7.1 | Preparation of a report on comparative assessment of different types of global practices on tertiary education, training, examination & certification processes
12.7.2 | Consultation with MiDA/SDAC on merits & demerits of different practices and selection of the certification process for Ghana
12.7.3 | Preparation of training modules & schedules for 4.5 days of training each for the SEMP & SEAP modules
12.7.4 | Development of PPT presentation for each of the two modules as per the syllabi
12.7.5 | Preparation of workbook with course administration guide
12.8 | Development of content for EAP course
12.8.1 | Listing of measuring instruments & equipments commonly used for energy audit & assessment of solar PV potential
12.8.2 | Preparing tip-sheets on 'how to deploy' these instruments for field measurement
12.8.3 | Preparing tip-sheets on handling of instruments-safety practices for personel as well as instruments
Preparing instruction sheets on formatting of data sheets and recording of measured data
12.8.4 | Preparing a manual containing all the instruction (Training manual)
12.8.5 | Preparation of training modules & schedules for 4.5 days of training each for the EAP module
12.9 | Design of certification examination formats
12.9.1 | SEMP
12.9.2 | SEAP
12.9.3 | EAP
12.9.4 | Stakeholders consultation-examination formats
12.9.5 | Finalisation of examination formats
| D 6.1- Report on Ghana SEMP Certification Course Content (Curriculum) |  |  | 12: W12
| D6.2- Report on Ghana SEAP Certification Course Content (Curriculum) |  |  | 12: W12
| D6.3- Report on Ghana EAP Course (Training manual) |  |  | 12: W12
12.1 | Certification exam development
12.10.1 | Review of various documents | bar: 12 to 14
Energy auditors certification examination program available in the public domain | bar: 12 to 14
Case study reports from consortium members | bar: 12 to 14
12.10.2 | Analysis of Pros and cons analysis-written test vs written test followed by viva
12.10.3 | Review of | bar: 14 to 16
Number of papers and scores | bar: 14 to 16
Common papers for all three courses and differentiated ones | bar: 14 to 16
Qualifying marks for passing and certification | bar: 14 to 16
Remedy in case of failures | bar: 14 to 16
Validity and process of revalidation | bar: 14 to 16
Physical vs. Online Examination | bar: 14 to 16
Proctoring for physical and online programs | bar: 14 to 16
Fee structure | bar: 14 to 16
12.10.4 | Development of instruction book | bar: 14 to 16
12.10.5 | Development of multiple choice questions-three versions each | bar: 14 to 16
12.10.6 | Stakeholders consultation | bar: 14
| SD-15: Presentation to SDAC on draft examination program |  |  | 16: W16
| D 7.1- Report on SEMP Course Certification Exam |  |  | 16: W16
| D 7.2-Report on SEAP Course Certification Exam |  |  | 16: W16
| D 7.3-Report on EAP Course Certification Exam |  |  | 16: W16
12.11 | Development of TOT Course Syllabi and TOT Courses
12.11.1 | Defining the training objectives for:
SESCs
Other potential training organisations
12.11.2 | Review & assessment
TOT course content
Course content delivery strategy & technique
Best practices for adult learning and classroom management
12.11.3 | Stakeholders consultation
12.11.4 | Finalisation of outline of TOT course and delivery system
| D8-Report on SE TOT Course Syllabi |  |  | 20: W19
12.11.5. | Review reports on training programs and TOT training programs of the consortium partners | bar: 20 to 22
12.11.6 | Development of methodology for evaluation of effectiveness TOT course | bar: 20 to 22
12.11.5. | Development of methodology for assessing performance of individual trainers | bar: 20 to 22
12.11.7 | Sensitivity analysis and design of review and feedback system | bar: 20 to 22
12.11.5. | Preparation of course contents | bar: 20 to 22
PPT presentation | bar: 22 to 24
Videos | bar: 22 to 24
Instruction and tip sheets | bar: 22 to 24
12.11.10 | Stakeholders consultation | bar: 22 to 24
12.11.12 | Finalisation of TOT course contents | bar: 22 to 24
| D9.1-Report on Ghana SEMP TOT Course Content |  |  | 24: W23
| D9.2-Report on Ghana SEAP Course Content |  |  | 24: W23
| D9.3-Report on Ghana EAP TOT Course Content |  |  | 24: W23
13 | Development of CFI /CFP to Host the SESCs
13.1 | Development of criteria for selection of SESC
13.1.1 | Review of status quo of the existing institutions providing tertiary education
History of development
Course material
Course delevery & examination process
Certification process
Faculty/trainers engaged in course delivery/training
Qualification criteria for selection of faculty
Qualification criteria for admission of students/trainee for the different courses
13.1.2 | Review of global status quo based on document available in the public domain/consortium
Criteria for affiliating training institutions
Qualification & experience criteria for candidates taking certification examination
13.1.3 | Develop a long list of criteria for initial screening of institutions
13.1.4 | Develop a long list of criteria for initial screening of training candidates for certification examination
13.1.5 | Assessment-weight factors (SEMP, SEAP, EAP)
13.1.6 | Develop weight factors for institutional scores & individual scores
13.1.7 | Develop overall scoring matrix
13.1.8 | Preparing recommendation report for SDAC for finalization of selection criteria | bar: 20 to 22
13.1.9 | Providing support to SDAC for finalization of the criteria | bar: 22
| SD-16: Recommendation report on criteria for screening of SESCs |  |  | 22: W16
13.2 | Assisting MiDA procurement agency in preparation of CFI/CFP documents & CFI/CFP management process
13.2.1 | Develop the technical contents and draft special conditions for the CFI as per MiDA RFP Template | bar: 22
13.2.2 | Prepare a list of institutions that can be directly invited for participation in the bid | bar: 22
13.2.3 | Prepare a list of other potential platforms for widening the participation of potential institutions in the process in consultation with SDAC | bar: 22
13.2.4 | Provide assistance to MiDA procurement agency | bar: 22
Evaluation of the CFI | bar: 22
Screeing of institutions | bar: 22
13.2.5 | Develop the technical contents and draft special conditions for the CFP as per MiDA RFP Template | bar: 22
13.2.6 | Assist MiDA procurement agency in preparation of the CFP document for final selection of SESCs | bar: 22
(Issue of difference between shortlist & selection to be got clarified as only 2 are supposed to have been shortlisted?) | bar: 22
| D10.1- Report on CFI for Candidate Organizations to Host the SESCs and Shortlisting |  |  | 26: W26
| D12.1- Supporting documentation to launch a CFP for Candidate Institutions to host the SESCs |  |  | 44: W44
| D10.2- Report on initial shortlisting of candidate SESCs and list of nominated training candidates |  |  | 34: W33
14 | Delivery of core certification courses
14.1 | Inviting participants | bar: 34
14.1.1 | Preparing the list of eligible candidates from the screened institutions for the certification examination | bar: 34
14.1.2 | Finalising the schedule & logistics as advised by MiDA | bar: 34
14.1.3 | Assist MiDA in inviting the participants along with delivery of course materials for them to prepare in advance | bar: 34
14.1.4 | Review of Reports on proctoring alternative models | bar: 36
Available in the public domain | bar: 36
Database of consortium partners | bar: 36
14.1.5 | Development of multiple choice questions (MCQs) from the course material | bar: 36
14.1.6 | Review of available laboratory, instruments and test facilities for EA examination | bar: 36
14.1.7 | Development of structured format for obtaining feedback | bar: 36
14.1.8 | Consultation with SDAC | bar: 36
14.1.9 | Finalization of course implementation plan | bar: 36
SD-17: Recommendation report on proctoring | bar: 36
14.2 | Delivery of the three courses | bar: 38
14.2.1 | Detailing of schedules for the individual courses | bar: 38
14.2.2 | Selection of faculties from the consortium | bar: 38
14.2.3 | Consultation meeting of all faculties with SDAC | bar: 38
14.2.4 | Finalisation of course delivery & examination process | bar: 38
14.2.5 | Delivery of the three courses to the selected examinees | bar: 38
14.4 | Conducting certification examination | bar: 38
14.4.1 | Finalisation of the proctoring methodology | bar: 38
14.4.2 | Facilitating taking of the examination by the candidates | bar: 38
14.4.3 | Scoring of results | bar: 38
14.4.4 | Preparing the result sheets along with recommendation report and submission to SDAC | bar: 38
14.4.5 | Assisting SDAC in announcing the results | bar: 38
| D11.1- Report on the Ghana SEMP course certification exam results |  |  | 40: W39
| D11.2- Report on the Ghana SEAP course certification exam results |  |  | 40: W39
| D11.3- Report on the Ghana EAP course certification exam results |  |  | 40: W39
14.5 | Review of course implementation
14.5.1 | Review of the courses, MCQs & examination process | bar: 40
14.5.2 | Review of the feedbacks received from candidates | bar: 40
14.5.3 | Identification of improvement needs | bar: 40
14.5.4 | Consultation with SDAC | bar: 40
| D11.4- Report on the SEMP course implementation |  |  | 40: W39
| D11.5- Report on the SEAP course implementation |  |  | 40: W39
| D11.6-Report on the EAP course implementation |  |  | 40: W39
14.6 | Selection of SESC
14.6.1 | Review of CFI score
14.6.2 | Review of candidate scores-certification examination | bar: 40
Assist MiDA procurement agancy in final shortlisting of SESC candidate for issue of CFP | bar: 40
| D11.7-Report on the final shortlisting of SESC candidate institutions |  |  | 42: W42
14.6.3 | Assisting MiDA procurement agency in: | bar: 44 to 46
Issue of CFPs to the shortlisted institutes | bar: 44 to 46
Evaluation of the proposals from shortlisted institutes against the CFP | bar: 44 to 46
preparing the composite & final score sheets | bar: 44 to 46
Rank ordering of the qualified candidates | bar: 44 to 46
14.6.4 | Development of draft ‘MOU’ to be signed between MiDA & the candidate institutions | bar: 44 to 46
14.6.5 | Facilitating interaction meetings between MiDA & selected institutions | bar: 48
14.6.6 | Facilitating signing of MOU | bar: 50
| D12.2-Report on the final selection of the SESCs host institutions |  |  | 50: W50
SD-18: Draft MOU | bar: 50
15 | Review and Recommendation of TOT Courses
15.1 | Conducting of TOT programs | bar: 52
15.1.1 | Detailing of schedules for the individual TOT programs | bar: 52
15.1.2 | Selection of faculties from the consortium | bar: 52
15.1.3 | Finalisation of course delivery & review process | bar: 52
15.1.4 | Assisting MiDA in finalising logistic arrangements | bar: 52
15.1.5 | Delivering the programs | bar: 52
15.3 | Review of the video tapes and candidate feedback | bar: 52
15.4 | Review of the courses | bar: 52
15.5 | Identification of improvement needs | bar: 52
15.6 | Consultation with SDAC | bar: 52
15.7 | Finalization of course implementation plan | bar: 54
| D13.1- Report on the SEMP TOT course implementation |  |  | 54: W54
| D13.2- Report on the SEPDP TOT course implementation |  |  | 54: W54
| D13.3 - Report on the EAEPT TOT course implementation |  |  | 54: W54
III | SERVICES TO OPERATIONALIZE SESCs AT SELECTED INSTITUTIONS AND DEVELOPMENT OF TERTIARY LEVEL EA COURSE CURRICULUM FRAMEWORK
16 | Business plan development
16.1 | Preparing the annotated outline of the plan and assisting SESC develop draft plan
16.1.1 | Review of the SESC roadmap
16.1.2 | Development strategy in line with roadmap
16.1.3 | Target market & business models
16.1.4 | Revenue plan
16.1.5 | Marketing plan
16.1.6 | Operation plan
16.1.7 | Organisation & human resource development plan
16.2 | Conducting business plan workshop
16.2.1 | Develop plan for business plan workshop | bar: 54
16.2.2 | Consultation with SDAC | bar: 54
16.2.3 | Conducting business planning workshop | bar: 54
16.3 | Handholding individual SESC for preparing its own business plan | bar: 56
16.4 | Facilitate presentation of business plan by individual SESC to SDAC & other key stakeholders | bar: 56
16.5 | Assist individual SESC in finalisation of the individual plans | bar: 56
SD-19: Draft business plan & report on business plan workshop | bar: 56
16.6 | Prepare report on task | bar: 58
| D14.1 Report on SESC Business Plans |  |  | 58: W58
17 | Operations plan development
17.1 | Defining the organisation entity
17.1.1 | Review of current academic and organisational relationship between the mother technical institutes and the tertiary education providers
17.1.2 | Review of different models for tertiary education services based on study of reports
From the net
Experience of the consortium partners
17.1.3 | Review of current policy/legal framework (if any) in Ghana regulating tertiary education services
17.1.4 | Stakeholders consultation
17.1.5 | Preparing recommendation report on organisation matrix for current & future SESCs
17.2 | Development of the internal organisation processes & procedures
17.2.1 | Review of operational processes for similar organisation globally | bar: 54
Interaction meeting with institutions authorities on the existing administrative processes & procedures | bar: 56
DESL operation manual | bar: 56
Experiential inputs from consortium partners | bar: 56
17.2.2 | Development of proposed internal processes | bar: 56
Human resource management and development including recruitment & training, induction, administrative procedures etc | bar: 56
Knowledge development & management-very important for service organisations | bar: 56
Management of infrastructures including hardwares & softwares | bar: 56
Administration, accounting, financial & governance | bar: 56
17.2.3 | Development of proposed external processes | bar: 56
Market & business development | bar: 56
Service deliveries | bar: 56
Engaging with key stakeholders-policy dialogue | bar: 56
17.3 | Preparation of report including templates, checklists
17.3.1 | Analysis of the current internal processes for organization management | bar: 54 to 56
17.3.2 | Development of operational plan template | bar: 54 to 56
17.3.3 | Assisting SESCs in documenting all the processes as per template and preparation of manuals | bar: 56 to 58
17.3.4 | Preparation of check lists | bar: 56 to 58
| D14.2-Report on SESC Operations Manuals |  |  | 58: W58
18 | Pilot SE retrofit project development supervision
18.1 | SE Pilot project development
18.1.1 | Review of data pertaining to shortlisted buildings | bar: 58 to 60
18.1.2 | Selection of facility in consultation with MiDA | bar: 58 to 60
18.1.3 | Formation of audit team | bar: 60
18.1.4 | Providing half a day refresher training on types of audit and use of portable instruments | bar: 60
18.1.5 | Review of availability of portable instruments | bar: 60
18.1.6 | Mentoring on: | bar: 60
Preparation of data formats and plan for data collection | bar: 60
Tabulation and organizing data collected | bar: 60
Conducting Field Measurements | bar: 60
Developing calculation routines | bar: 60
Assessment of energy consumption baseline | bar: 60
Identification of energy saving projects | bar: 60
Developing M&V Plan | bar: 60
Project implementation strategy development | bar: 60
Preparation of report & presentation | bar: 60
18.1.7 | Review post completion of audit | bar: 62 to 64
18.1.8 | Quality of presentation & reports | bar: 64
| D15.1- Report on Critique of the Walk-Through Energy Audits for Each Facility Assigned to Each of the SESCs. |  |  | 64: W64
| D15.2-Report on Critique of the Investment Grade Energy Audits for Each Facility Assigned to Each of the SESCs. |  |  | 64: W64
| D15.3-Report on Critique of the Project Implementation Plans for Each Facility Assigned to Each of the SESCs. |  |  | 64: W64
| D15.4-Report on Critique of the Measurement and Verification Plans Developed for Each Facility Assigned to Each of the SESCs. |  |  | 64: W64
| D15.5-Report on Critique of the finance plan for implementation of SE projects. |  |  | 64: W64
| D15.6-Report on Critique of tender documentation for procurement of design and construction services to implement the SE projects. |  |  | 64: W64
| D15.7- Summary report detailing all the project development documents for the Pilot SE Projects |  |  | 64: W64
18.2 | Delivery of SE Courses by SESCs
18.2.1 | Assisting in design of the course based on finding from the audits | bar: 58
18.2.2 | Identification of volunteer facility for course delivery | bar: 58
18.2.3 | Assisting SESCs in reviewing and if necessary, modifying the course contents based on learnings from the pilot audits | bar: 58
18.2.4 | Development of the performance evaluation criteria and sensitizing the trainers | bar: 58
18.2.5 | Selection of the first facility for course delivery in our presence | bar: 58
18.2.6 | Review of observations made during the course delivery | bar: 60
18.2.7 | Review of the Videograph | bar: 62 to 64
18.2.8 | Preparation of review reports | bar: 62 to 68
| D16.1- Report on Written Critique for each of the two SE courses delivered by each of the SESC |  |  | 68: W67
| D16.2- Report on Critique of the videotaped playback for each of the two SE courses delivered by each of the SESC |  |  | 68: W67
IV | Project Closure
19 | Develop final completion reports for setting up SESC
19.1 | Review of SESC Road Map | bar: 68 to 70
19.2 | Preparation of final report | bar: 68 to 70
SD 20: Final report on SESC roadmap | bar: 70
SD 21: Final report on SES program roadmap | bar: 70
| D-17- Develop final completion reports for summarizing Part I – III |  |  | 70: W70
End of L3 list | bar: 70
DELIVERABLES
1 | Submission of Kick off Meeting Notes | W1
2 | Report on Inception Mission Workshop and Inception Report
2.1 | Report on Inception Mission Workshop | bar: 4
2.2 | Submission of Draft Inception Report | bar: 4
2.3 | Submission of Inception Report | bar: 4
3 | Preparation of National Sustainable Energy Centre Roadmap
3.1 | Report on Ghana SE Market Transformation Needs Assessment | bar: 8
3.2 | Report on SE Services Stocktaking and Gaps Assessment | bar: 8
3.3 | Report on Baseline Review and Gap Assessment of Tertiary SES education programs in Ghana | bar: 8
3.4 | Report on SESC Roadmap |  |  | 12: W12
3.5 | Report on the Tertiary level SES Program Roadmap |  |  | 12: W12
4 | Delivery of National SE Market Accelerator Conference and Regional SE Technology Showcase
4.1 | Report on Design and Implementation Plan for the National SE Market Accelerator Conference |  |  | 16: W16
4.2 | Report on Design and Implementation Plan for the National SE Technology Showcase |  |  | 16: W16
4.3 | Report on Implementation Plan Report for the National SE Market Accelerator Conference and SE Technology Showcase. |  |  | 16: W16
4.4 | Report on Final Part I Dissemination Workshop |  |  | 20: W19
5 | Report on Sustainable Energy Course Development Syllabi | bar: 8
6 | Sustainable Energy Course Content
6.1 | Report on Ghana SEMP Certification Course Content |  |  | 12: W12
6.2 | Report on Ghana SEAP Certification Course Content |  |  | 12: W12
6.3 | Report on Ghana EAP Course |  |  | 12: W12
7 | Sustainable Energy Course Certification Exams and Proctoring Instructions
7.1 | Report on SEMP Course Certification Exam |  |  | 16: W16
7.2 | Report on SEAP Course Certification Exam |  |  | 16: W16
7.3 | Report on EAP Course Certification Exam |  |  | 16: W16
8 | Report on SE TOT Course Syllabi |  |  | 20: W19
9 | Sustainable Energy Course TOT Content
9.1 | Report on Ghana SEMP TOT Course Content |  |  | 24: W23
9.2 | Report on Ghana SEAP Course Content |  |  | 24: W23
9.3 | Report on Ghana EAP TOT Course Content |  |  | 24: W23
10 | SESC CFI and Selection Criteria for Shortlisting
10.1 | Report on CFI for Candidate Organizations to Host the SESCs and Shortlisting |  |  | 26: W26
10.2 | Report on initial shortlisting of candidate SESCs and list of nominated training candidates |  |  | 34: W33
11 | Report on Certification Examination Results, Course Implementation and final shortlisting of SESC Candidate Institutions
11.1 | Report on the Ghana SEMP course certification exam results |  |  | 40: W39
11.2 | Report on the Ghana SEAP course certification exam results |  |  | 40: W39
11.3 | Report on the Ghana EAP course certification exam results |  |  | 40: W39
11.4 | Report on the SEMP course implementation |  |  | 40: W39
11.5 | Report on the SEAP course implementation |  |  | 40: W39
11.6 | Report on the EAP course implementation |  |  | 40: W39
11.7 | Report on the final shortlisting of SESC candidate institutions |  |  | 42: W42
12 | Launch of CFP for Hosting the SESCs
12.1 | Supporting documentation to launch a CFP for Candidate Institutions to host the SESCs |  |  | 44: W44
12.2 | Report on the final shortlisting of the SESCs host institutions |  |  | 50: W50
13 | TOT Implementation Report
13.1 | Report on the SEMP TOT course implementation |  |  | 54: W54
13.2 | Report on the SEPDP TOT course implementation |  |  | 54: W54
13.3 | Report on the EAEPT TOT course implementation |  |  | 54: W54
14
14.1 | Report on SESC Business Plans |  |  | 58: W58
14.2 | Report on SESC Operations Manuals |  |  | 58: W58
15 | Critique on Project Development Documents for the Pilot SE Projects
15.1 | Report on Critique of the Walk-Through Energy Audits for Each Facility Assigned to Each of the SESCs. |  |  | 64: W64
15.2 | Report on Critique of the Investment Grade Energy Audits for Each Facility Assigned to Each of the SESCs. |  |  | 64: W64
15.3 | Report on Critique of the Project Implementation Plans for Each Facility Assigned to Each of the SESCs. |  |  | 64: W64
15.4 | Report on Critique of the Measurement and Verification Plans Developed for Each Facility Assigned to Each of the SESCs. |  |  | 64: W64
15.5 | Report on Critique of the finance plan for implementation of SE projects. |  |  | 64: W64
15.6 | Report on Critique of tender documentation for procurement of design and construction services to implement the SE projects. |  |  | 64: W64
15.7 | Summary report detailing all the project development documents for the Pilot SE Projects (Deliverables 15.1 – 15.6) |  |  | 64: W64
16 | Critique of the SE Course Delivery
16.1 | Report on Written Critique for each of the two SE courses delivered by each of the SESC |  |  | 68: W67
16.2 | Report on Critique of the videotaped playback for each of the two SE courses delivered by each of the SESC |  |  | 68: W67
17 | Develop final completion reports for summarizing Part I – III |  |  | 70: W70
[5 empty] | Home |  |  | Field |  |  | Sub-Deliverable |  |  |  |  | W70 | Deliverable
Abbreviations Used
DSM | Demand Side Management
EA | Energy Audit
EAP | Energy Audit Practical Course
EE | Energy Efficieincy
GES | Ghana Education Services
IEA | International Energy Agency
KPI | Key performance indicators
SDAC | SESC Development Advisory Committee
SE | Sustainable Energy
SEAP | Sustainable Energy Audit Professional course
SEMP | Sustainable Energy Management Professional course
SES | Sustainable energy services
SESC | Sustainable Energy Service Centre

## Inception phase tasks
Data collection/survey
Ref | Particulars
1.2.3 | Market potential for SE products | DESL/MSME/Traders/Manufaturers
1.2.4 | Market potential for SE services | Building FM/MSME industry/Utility
1.2.5 | Need for market transformation | Traders/MOE/EC/EF
1.2.6 | Investment potential for SE products & services-MSME industries | DESL/EF/Development partners
1.2.7 | Investment potential for SE products & services-buildings | DESL/EF/Development partners
1.2.8 | Potential for distributed solar PV system for buildings | DESL/EF/Development partners
1.2.9 | Investment potential for solar PV systems in buildings | DESL/EF/Development partners
1.2.10 | Availability of SE products | Traders/Manufacturers/Building FM
1.2.11 | Need for and availability of SE services
1.2.12 | Tertiary education system for EE & RE services | EC/EF/Institutes
6.1.10 | Assessment of other enabling environment for promotion of SE market such as:
| Government policies | MOE/EC
| Legal & regulatory instruments | EC
| Utility DSM programs | EC/EF/Utility
| Utility tariff | EC
| Availability & access to finance | Building FM/MSME/Banks
| Availability & reliability of SE products & services | Building FM
Consumer capacity to absorb SE technologies
6.1.11 | Identification of current sources of sustainable energy services financing available in the market and complimentary technical assistance schemes | EF/Banks/Development partners
6.1.12 | Assessment of status quo on absorption of available finance in SE projects | Banks
6.1.13 | Assessment of capacity of the lenders to appraise and finance SE projects | Banks
6.1.14 | Identification and assessment of any innovative financial product that has been introduced in the Ghana market in the last five (5) years | Banks/Development partners
6.1.15 | Assessment of overall institutional framework for development of SE market
6.3.1 | Review
| Contry stratgic & operational plan for the energy sector | MOE/EC
Impact of energy availability & cost on economic development
| Country strategy on combating climate change | MOE/EC
| Legal & regulatory initiatives on SE development | MOE/EC
| Strategy for EE and RE (Solar PV) | EC/EF
7.2.7 | Client feedback for services | Building FM
7.2.8 | Market awareness-qualification & experiences of current SE service providers | Building FM
7.2.9 | Assessment of capacity to provide services under different models | Building FM
7.2.10 | Assessment of quality of reports and improvements needed | Building FM
8.1.1 | Conducting structured survey for assessing the need for skilled professional by the SE service providers in the following domains: | Accessing a list of SE service providers
SE related professional organizations (e.g. areas such as architecture, engineering).
Existing, major SE related service Consultant or organizations.
SE related equipment suppliers (e.g. HVAC, pumps, solar systems, etc.).
Utility demand side management organizations.
Development partners.
8.3.1 | Summarise the findings from the interaction meetings with key stakeholders (including institutions & alumnus) on tertiary education during inception mission
8.3.2 | Review of reports, documents collected during the inception mission on tertiary education
| Course curriculum, syllabi,training program, examination and certification program provided by recognised institutions | Technical institutes/ECREEE
| Other training programs conducted by development partners, private bodies | Technical institutes/ECREEE
| Historical development-tertiary education for SE services | Technical institutes/ECREEE
8.3.3 | Review & analysis-objective of the current pograms on tertiary education
8.3.4 | Assessment of the effectiveness of the current programs against identified needs
8.3.5 | Informal interaction with few identified alumnus & other SE service providers on the findings | Finding contacts (ECREE ?)
8.4 | Assessment of capacity of existing educators & capacity building need
8.4.1 | Conducting primary survey and confidential interviews | Technical institutes/ECREEE
8.4.2 | Assessment of capacity to meet the demand for tertiary education | Technical institutes/ECREEE
9.2.1 | Assessment of ‘ready-to-go’ SE market for different services in Ghana: | Screened out lists post trade show
SE services
SE tertiary education services
Training & development of SE service providers
Policy research, analysis & dialogue
Legal & regulatory research & analysis
Promotional activities
9.2.2 | Identification and evaluation of potential revenue earning streams from SE services | Development partners
11.1.3 | Preparing database of potential participants
11.1.4 | Review & assessment of facilities/support expected by participants for attending the program | Physical assessment
11.1.5 | Review of options for venue & logistics | Physical assessment
11.1.6 | Identification of potential event manager for organising & managing the shows | Physical assessment
12.2 | Review the qualification and experience of the professionals currently engaged with SE service providers (part of structured survey)
12.3 | Review and assess the availability of professionals & their qualification & experience (from primary survey data)
13.1.1 | Review of status quo of the existing institutions providing tertiary education | (Survey form ref 8.4)
History of development
Course material
Course delevery & examination process
Certification process
Faculty/trainers engaged in course delivery/training
Qualification criteria for selection of faculty
Qualification criteria for admission of students/trainee for the different courses
17.1.1 | Review of current academic and organisational relationship between the mother technical institutes and the tertiary education providers
17.1.3 | Review of current policy/legal framework (if any) in Ghana regulating tertiary education services

## SES providers
International Energy Services Limited Ghana
1
2 | SGS
Airport Residential Area,
Accra
Ghana
T+233 302 77 39 94 / 95
F+233 302 77 90 75
3 | AFA, Ghana
King Lumor
Phone: (233) 201 885 560
Email: klumor@afaghana.com

## Survey interview plan
Survey/ consultation with stake holders
| Survey/interviews |  | Stakeholders for survey/consultation/interviews
|  | Formats | Traders/Mfrs | Building FM | MSME | Tech Inst | EC | MOE | PURC | MOEST | NBSSI | NCTE | NBPTE | ECG | KNUST | SES providers | EF | ECREEE | AGSI | GGBC | Banks/Fis | ACEP | NEDCo | VRA | GNCC | GIPC | ERERA | GSA
1.2.3 | Market potential for SE products | Market survey | x | x | x | [10 empty] | x | x | x | x | x | bar: EC; NBSSI
1.2.4 | Market potential for SE services | SE services KPIs |  | x | x | [10 empty] | x | x | x |  | x | bar: EC; NBSSI
1.2.5 | Investment potential for SE products & services-MSME industries | Audit reports | x |  | x | [10 empty] | x | x | x |  |  | x | bar: EC to MOE; NBSSI; ECG
1.2.6 | Investment potential for SE products & services-buildings | Audit reports | x | x | [11 empty] | x | x | x |  | x | x | bar: EC to MOE
1.2.7 | Potential for distributed solar PV system for buildings | Format to be prepared | x | x | [14 empty] | x | x | xx
1.2.8 | Investment potential for solar PV systems in buildings |  | x | x | [14 empty] | x
1.2.9 | Availability of SE products | Market survey |  | x | x
1.2.10 | Need for and availability of SE services | Interviews |  | x | x | x | [9 empty] | x | x | x | bar: EC to MOE; MOEST; ECG to KNUST
1.2.11 | Tertiary education system for EE & RE services | As per 8.3.2 |  | x | x | x | [9 empty] | x | x | x | bar: EC to MOE; MOEST; NCTE to NBPTE
1.2.12
6.1.10 | Assessment of other enabling environment for promotion of SE market such as:
| Government policies | Interviews-status report (Rules, schedules, implementation) |  |  |  | x | [10 empty] | x | x | x | x | x | bar: EC to MOEST
| Legal & regulatory instruments | Interviews-status report (Rules, schedules, implementation) | [14 empty] | x | bar: EC to PURC
| Utility DSM programs | Reports | bar: EC
| Utility tariff | Latest tariff order | bar: EC to PURC
| Availability & access to finance | Interviews/Bank schemes
| Availability & reliability of SE products & services |  | x | x | x | [10 empty] | x | x |  |  |  | x | bar: NBSSI; ECG
| Consumer capacity to absorb SE technologies | Interviews | x | x | x
6.1.11 | Identification of current sources of sustainable energy services financing available in the market and complimentary technical assistance schemes | Banks schemes | [18 empty] | x
6.1.12 | Assessment of status quo on absorption of available finance in SE projects | Interviews-Banks | [18 empty] | x
6.1.13 | Assessment of capacity of the lenders to appraise and finance SE projects | Interviews-Banks | [18 empty] | x
6.1.14 | Identification and assessment of any innovative financial product that has been introduced in the Ghana market in the last five (5) years | Interviews-Banks | [18 empty] | x
6.1.15 | Assessment of overall institutional framework for development of SE market | Interviews | [14 empty] | x | x | x | x | bar: EC to NBSSI
6.3.1 | Review
| Contry stratgic & operational plan for the energy sector | Policy document | bar: EC to MOEST
| Impact of energy availability & cost on economic development | Available reports/Interviews | bar: EC to MOEST
| Country strategy on combating climate change | Available reports/Interviews | bar: EC to MOEST
| Legal & regulatory initiatives on SE development | Available reports/Interviews | bar: EC to MOEST
| Strategy for EE and RE (Solar PV) | Available reports/Interviews | bar: EC to MOEST
7.2.7 | Client feedback for services | Fomats to be prepared
7.2.8 | Market awareness-qualification & experiences of current SE service providers | Fomats to be prepared |  | x | x | [10 empty] | x | x | x
7.2.9 | Assessment of capacity to provide services under different models | Fomats to be prepared |  | x | x | [10 empty] | x | x | x
7.2.10 | Assessment of quality of reports and improvements needed | Copies of reports |  | x | x | [10 empty] | x | x | x
8.1.1 | Conducting structured survey for assessing the need for skilled professional by the SE service providers in the following domains:
| SE related professional organizations (e.g. areas such as architecture, engineering). | SES KPI formats |  | x | x | [10 empty] | x | x |  | x | x | bar: EC; ECG to KNUST
Existing, major SE related service Consultant or organizations.
| SE related equipment suppliers (e.g. HVAC, pumps, solar systems, etc.). | Market survey | x | x | x | [10 empty] | x |  |  | x | x | bar: ECG
| Utility demand side management organizations. | Interviews | [14 empty] | x | bar: EC to MOE
| Development partners. | Interviews | [15 empty] | x
8.3.1 | Summarise the findings from the interaction meetings with key stakeholders (including institutions & alumnus) on tertiary education during inception mission
8.3.2 | Review of reports, documents collected during the inception mission on tertiary education
| Course curriculum, syllabi,training program, examination and certification program provided by recognised institutions | Reports/data to be collected |  |  |  | x | [11 empty] | x | bar: NCTE to NBPTE
| Other training programs conducted by development partners, private bodies | Reports/data to be collected |  | x | x | [12 empty] | x | bar: KNUST
| Historical development-tertiary education for SE services | Reports/data to be collected |  |  |  | x | bar: NCTE to NBPTE
8.3.3 | Review & analysis-objective of the current pograms on tertiary education | Interviews
8.3.4 | Assessment of the effectiveness of the current programs against identified needs | Interviews
8.3.5 | Informal interaction with few identified alumnus & other SE service providers on the findings | Interviews |  | x |  | x | [9 empty] | xx
8.4 | Assessment of capacity of existing educators & capacity building need |  |  |  |  | x
8.4.1 | Conducting primary survey and confidential interviews | Formats to be prepared |  |  |  | x
8.4.2 | Assessment of capacity to meet the demand for tertiary education |  |  |  |  | x | bar: NCTE to NBPTE
9.2.1 | Assessment of ‘ready-to-go’ SE market for different services in Ghana:
| SE services | Interviews |  | x | x | [10 empty] | x
| SE tertiary education services | Interviews |  |  |  | x | [9 empty] | x
| Training & development of SE service providers | Interviews
| Policy research, analysis & dialogue | Interviews
| Legal & regulatory research & analysis | Interviews
| Promotional activities | Interviews
9.2.2 | Identification and evaluation of potential revenue earning streams from SE services
11.1.3 | Preparing database of potential participants
11.1.4 | Review & assessment of facilities/support expected by participants for attending the program
11.1.5 | Review of options for venue & logistics
11.1.6 | Identification of potential event manager for organising & managing the shows
12.2 | Review the qualification and experience of the professionals currently engaged with SE service providers (part of structured survey)
12.3 | Review and assess the availability of professionals & their qualification & experience (from primary survey data)
13.1.1 | Review of status quo of the existing institutions providing tertiary education
| History of development | Reports/data |  |  |  | x
| Course material |  |  |  |  | x
| Course delevery & examination process |  |  |  |  | x
| Certification process |  |  |  |  | x
| Faculty/trainers engaged in course delivery/training |  |  |  |  | x
| Qualification criteria for selection of faculty |  |  |  |  | x
| Qualification criteria for admission of students/trainee for the different courses |  |  |  |  | x
17.1.1 | Review of current academic and organisational relationship between the mother technical institutes and the tertiary education providers |  |  |  |  | x | bar: NCTE to NBPTE
17.1.3 | Review of current policy/legal framework (if any) in Ghana regulating tertiary education services |  |  |  |  | x | bar: NCTE to NBPTE
ACEP | African center for energy policy, Ghana
Traders/Mfrs | Traders/ Manufacturers
Building FM | Building facility managers
MSME | Micro small medium enterprises
Tech Inst | Technical institutes
EC | Energy commission
MOE | Minisry of Education
PURC | Public utilities regulatory commission
MOEST | Ministry of environment, science and technology
NBSSI | National board for small scale industries
NCTE | National council for tertiary education
NBPTE | National board for professional and technical education
ECG | Electricity company of Ghana
KNUST | Kwame Nkrumah University of Science and Technology
SES providers | Sustainable enrgy service providers
EF | Energy foundation
ECREEE | Ecowas center for renewable energy and energy efficiency
AGSI | Association of Ghana solar industries
GGBC | Ghana Green Building Council
Banks/Fis | Banks / Financial institutions
ACEP | Africa center for energy policy, Ghana
NEDCo | Northern electricity distribution company
VRA | Volta river authority
GNCC | Ghana national chamber of commerce
GIPC | Ghana Investment promotion center
ERERA | Ecowas regional electricity regulation authority
GSA | Ghana Standard Authority